## Sheet1
COMPLETED | DATE
CONTRACT
X | 2025-08-05 |  | Email Contract
X | 2025-08-06 |  | Colorado contract
Save Contract as PDF to Membership Accounting
X | 2025-05-20 |  | Contract PDF on ContractPage
X | 2025-05-28 |  | Add Legal Guardian Info to Contract and PDF
X | 2025-08-20 |  | Move CC authorize to CC Payment Screen
X | 2025-08-10 |  | Is this correct in emails? Includes monthly dues, add-ons, and applicable taxes
CC PROCESSING
X | 2025-05-21 |  | Online Windows Server
Credit card process
Credit Card Test Account
CONVERGE
FLUIDPAY
X | 2025-07-30 |  | Enter Token into strcustr
X | 2025-07-30 |  | Save CC last 4 digits and cvv exp date
X | 2025-07-30 |  | Submit Transaction Data to BOSS
X | 2025-07-30 |  |  | Create asptheade transaction number
X | 2025-07-30 |  |  | enter asptitemd and aspttendd after
|  | TABLES |  |  | Insert Membership information into Web tables
X | 2025-07-30 |  | INSERT asprecdoc |  | After the CC is processed, perform a qry of the cust_code to make sure it is still available
X | 2025-07-30 |  | INSERT ALL WEB TABLES |  |  | if not available get new one and update web table
X | 2025-07-30 |  | Move all data from Web tables to Production |  |  | if available continue
X | 2025-07-30 |  | Taxes in asprecdoc? Seems mixed on existing - ask John/Mel |  | Insert Membership information into Production tables
offer PIN/Password to customer
Insert Transaction into Transaction tables with this cust_code
|  | ONLINE DRAWER |  |  | So, half the data is being stored in web and transaction tables go straight to production
X | 2025-05-01 |  | Create ONLINE Boss account
X | 2025-07-30 |  | Script to OPEN / CLOSE Drawer
PT
X | 2025-06-03 |  | Ads for PT?
MISC
Ifee for Online? JoAnna? Add a For Web column in ifee table?
Prorate $0 ? How do we implement this?
X | 2025-05-20 |  | Addons per Club in table
Connect to Existing Wellbridge Website
X | 2025-07-30 |  | Update text on Enrollment Confirmation
Adding multiple youths and children need to be put back
X | 2025-05-21 |  | Confirm if 14 Day Term starts on Signature Date or Start Date |  | Start Date per John P
X | 2025-06-03 |  | Changing Membership Type isn't always clearing?
X | 2025-05-20 |  | Tax Rate from BOSS and apply to pages
X | 2025-05-21 |  | Start Date can not be greater than 7 days from signup.
X | 2025-08-10 |  | Add Descriptive popups for Addons - what they are
X | 2025-08-20 |  | Kids names need to be upper case
X | 2025-09-09 |  | Remove just Dues from colorado contract and show total only
X | 2025-09-09 |  |  | add (applicable taxes not included)
X | 2025-09-09 |  | Both contracts need to say Enrollment Fee and show the value
Need to add Ifee to items being sent to database, need to get the upc code
Add dropdown for Sales Reps to main page
Add Club logos to contracts
NANNY
Nanny only applies if Child/Youth have been added to Membership
Nanny requires enter the Nanny info as a Dependent to the Account with their Info
Nanny turns membership into Family in New Mexico or Dual in Colorado
UNLIMITED CHILD CARE
Unlimited Child Care in NM applies directly to the number of Children added to the membership, so 3 kids = 1,2,3 Unlimited as options & Only applies to 11 and under kids
SYP
SYP in Colorado can have Couple SYP or Individual with multiple children
SYP in New Mexico is Individual Only
JUNIOR
181818 Junior has different options
CLEANUP
Remove extra text from shopping cart
Remove CC Processor text from PaymentPage
Remove any logs that may show data in the browser
Remove Payment Method CC on Contract Page before contract