## Sheet1
COMPLETED | DATE | CLEANUP
Remove extra text from shopping cart
Remove CC Processor text from PaymentPage
Remove any logs that may show data in the browser
Remove Payment Method CC on Contract Page before contract
CONTRACT
Email Contract
Save Contract as PDF to Membership Accounting
X | 2025-05-20 |  | Contract PDF on ContractPage
X | 2025-05-28 |  | Add Legal Guardian Info to Contract and PDF
CC PROCESSING
X | 2025-05-21 |  | Online Windows Server
Credit card process
Credit Card Test Account
CONVERGE
FLUIDPAY
Enter Token into strcustr
Save CC last 4 digits and cvv exp date
Submit Transaction Data to BOSS
Create asptheade transaction number
enter asptitemd and aspttendd after
TABLES
INSERT asprecdoc
Move all data from Web tables to Production
ONLINE DRAWER
X | 2025-05-01 |  | Create ONLINE Boss account
Script to OPEN / CLOSE Drawer
NANNY
Nanny only applies if Child/Youth have been added to Membership
Nanny requires enter the Nanny info as a Dependent to the Account with their Info
Nanny turns membership into Family in New Mexico or Dual in Colorado
UNLIMITED CHILD CARE
Unlimited Child Care in NM applies directly to the number of Children added to the membership, so 3 kids = 1,2,3 Unlimited as options & Only applies to 11 and under kids
SYP
SYP in Colorado can have Couple SYP or Individual with multiple children
SYP in New Mexico is Individual Only
JUNIOR
181818 Junior has different options
PT
Ads for PT?
MISC
Ifee for Online? JoAnna? Add a For Web column in ifee table?
X | 2025-05-20 |  | Addons per Club in table
Connect to Existing Wellbridge Website
Update text on Enrollment Confirmation
Prorate $0 ? How do we implement this?
Adding multiple youths and children need to be put back
X | 2025-05-21 |  | Confirm if 14 Day Term starts on Signature Date or Start Date |  | Start Date per John P
Changing Membership Type isn't always clearing?
X | 2025-05-20 |  | Tax Rate from BOSS and apply to pages
X | 2025-05-21 |  | Start Date can not be greater than 7 days from signup.
Add Descriptive popups for Addons - what they are